## event checklist
| 2023 Event |  | Legend - Who does what
Event Chairs (Chair)
| Dates |  | Lead Comp Steward (Comp)
Lead Tech Steward (Tech)
| Forecast | type "n/a" as needed | Lead Grid Steward (Grid)
Racers |  |  | T&S Steward
TT |  |  | CR event promotion (Promo)
CRS |  |  | License Administrator (Lic)
Running a good track event happens because of the capabilities of the team and the preparation that came before getting to the track. Thank you for the prep!
Who | weeks b4 | What
Chair | 6 | Race is sanctioned
Chair | 6 | Chapter (or CR) wants and has an event sponsor (trophies, sponsor flag, social media promo)
Lic | 6 | Contingency awards, banners and all sponsor items available
Chair | 6 | BMW CR Stewards - hotels??
Chair | 4 | The preliminary schedule is available to CR for planning and promotion
Chair | 4 | The track will be ready - flaggers in alignment with sanction agreement
Chair | 4 | BMW CCA event insurance obtained - Toyo & Tire Rack are Named Insured
Chair | 4 | For Time Trials, classroom arranged
Grid | 4 | Grid and grid safety check plans agreed (sample plans are in separate tabs in this spreadsheet)
Chair | 4 | For Time Trials, does T&S have transponder number assignments?
Chair | 4 | Everything needed from National office is on order or in hand (see "need from National" tab)
Chair | 4 | Early event access to tower and meetng areas arranged
Comp | 4 | Sanction agreement & crisis response plans reviewed - driver mtg min standard reviewed, rookie & provisional day two meeting planned
Comp | 4 | Split start - yes or no and which races
Comp | 4 | Driver mtg min standard reviewed, rookie & provisional day two meeting planned
Chair | 4 | Grid / tech volunteers signed up (CR reserves the right to send additional staff at partner expense)
Tech | 4 | Compliance plan for event ready - scales available, impound location ok - tech supplies ok
T&S | 4 | Timing and scoring equipment ready (including printer)
T&S | 4 | Using RaceHero - good to go?
Promo | 4 | Trophies on order and ship to location clear? (for competitive classes - stickers also to winners)
Promo | 4 | Event pictures and Roundel reporting arranged - sponsor contingency award winner pics arranaged
Grid | 4 | Paddock and grid management agreed
Lic | 3 | Contingency awards, volunteer shirts, banners and all sponsor items shipped at least 3 weeks in advance
Chair | 2 | Send the event supplement with schedule to drivers
T&S | 2 | License status report complete (Membership, Comp, rookie, provisional, probation)
Chair | 1 | Pace car, trained driver, ride along observer and lights arranged
Chair | at the event | Sponsor banners ALL are prominently posted
T&S |  | Text app up and running
T&S |  | Reinforce need to know who's in the car for all sessions
Comp |  | Stewards - use current documents and T&S ready for video upload duty
Comp |  | If HPDE running at the same weekend, disallow CR drivers from running in DE sessions
Comp |  | Flaggers all present - safety not compromised
Comp |  | Cover driver's meeting minimum standard sep tab; use stickers to prove required attendance
Comp |  | Recap crisis response with event chair
Comp |  | Ensure the Optima selfie pic is provided before giving the Optima contingency to the winner
Comp |  | If HPDE running at the same weekend, disallow CR drivers from running in DE sessions
Grid |  | Confirm grid plan/wrist band checks with volunteers and track grid marshals
Tech |  | Announce schedule for scales over PA and on the text app
Tech |  | Work the compliance plan
All stwrds |  | Provide feedback to comp steward on CR equipment or process problems

## Need from National
CR Supplies required for track events
| Date requested | Date sent
Item | # Chair requires | # LA sent | Race | CRS | TT | Comments
Sponsor decal package |  |  | X |  | X | If there is a CRS before a Race, consider grads that need decals
Contingency Awards |  |  | X | X | X
CR flag |  |  | X | X | X
Medium CR Decals |  |  | X | X | X
Small CR Decals |  |  | X | X | X
Release Waivers |  |  | X | X | X
Class Winner Stickers |  |  | X |  | X
Set of Premier sponsor banners |  |  | X
Track tech Stickers |  |  | X
Annual Tech Stickers |  |  | X
Grid Marshal checklist on lanyard |  |  | X
Attendance stickers - Driver's meeting |  |  | X
Impound signs |  |  | X
Event tech stickers |  |  | X
Logbooks |  |  | X |  |  | If there is a CRS before a Race, consider grads that need logbook
Helmet ok stickers |  |  | X
Manila envelopes for incidents |  |  | X |  |  | Large and small coin envelopes for video cards
Redline Decals |  |  |  | X | X
Time trial Decals |  |  |  | X | X
Redline Banner |  |  |  | X | X
Bimmerworld Banner |  |  |  | X
Graduation Certificates (Chair to identify # of blank extra inaddition to those printed with Student names) |  |  |  | X |  | At approx. 2 wks prior, print certificates with names of registered students. Plus blank extras for last minute students.
Name tags |  |  |  | X
Bimmerworld Decals |  |  |  | X
Sharpie Pens |  |  |  | X
School Workbooks |  |  |  | X
Bimmerworld flyers |  |  |  | X

## sample grid comm plan
EVENT | Watkins Glen |  |  | Expected race entries | 80
Event dates | 9/23/22 to 9/25/22
| Day | Time | Text message topic |  | Special info for communication at this race
|  |  |  | RH | PA ?
| Thursday | 17:00 | Welcome-- registration and tech open hours ( 6:00-8:00 ) Gate 3 and Garage #17 | Yes
| Thursday | 7:00 PM | Announce Friday -Reg/Tech /Racers Meeting / 1st session | Yes
| Friday | first thing | Welcome -Registration and tech 7:00-8:00 AM | Yes
| Friday | 7:00 | Mandatory driver's meeting - 7:30 am Media Center | Yes
| Friday | 8:15 | P2W & Open Scales 8:30 AM-9:15 AM --Add Paddock Crawl info | Yes
| Friday | 9:30 | BMW Practice 10:10 AM -- Grid open 9:45 AM | Yes | If Avail
| Friday | 11:00 | Open Scales 11:15-12:15 | Yes
Impound 2:00-2:30 PM
| Friday | 12:30 | BMW Qualifying 1:25 pm - -Grid open 1:05 PM | Yes | If Avail
| Friday | 15:00 | BMW Sprint race -- 3:45 PM - Grid open 3:20 PM--Paddock Crawl reminder | Yes | If Avail
| Friday |  | IMPOUND 4:20 PM-4:50 PM
| 1 | track cold | Will or wont be a driver's meeting next day - details if needed | Yes
| Sat | first thing | Welcome to day 2 - Scales / Drivers meeting? / Misc info | Yes
| Sat | 7:00 AM ish | Scales Open 8:00-9:00 AM | Yes
| Sat | 9:00 AM | BMW Practice / Race? -- 10:10 AM -- Grid open 9:50 AM | Yes | If Avail
| Sat | 10:30 | BMW Qualifying -- 11: 00 AM -- Grid opens 10:40 AM | Yes | If Avail
| Sat | 13:00 | BMW Sprint Race -2:00- Grid opens 1:35 PM -- | Yes | If Avail
Impound 2:30 -3:30 PM
| Sat | 15:00 | BMW Sprint Race -3:40 PM Grid opens 3:15 PM -- | Yes | If Avail
| Sat | 4:45 ish | Awards Ceremony Reminder -- Location TBD | Yes
| Sunday | first thing | Welcome to day 3 - | Yes
|  |  | Scales open 9:00-9:30 AM | Yes
| Sun | 10:15 | BMW SPRINT RACE 11:20 AM-- Grid open 10:45 AM | Yes | If Avail
| Sun |  | Scales open 9:00 -10:00 AM
| Sun | 12:00 | BMW Enduro Race 1:00 PM -- Grid opens 12:35 PM | Yes | If Avail
IMPOUND 2:15-2:30 PM
| Sun | post race |  | Yes | If Avail
| Sun | post race | Safe home thank you for racing with BMW CCA Club Racing